## Sheet1
Poornima College of Engineering Department of Information Technology Product Backlog (Project-II: 2018-19)
Epic | Sprint | User Story | Story Details | Task Items | Analyst/Prep work | Dev. Est | QA | User Story hours
TMS | 1 | DevTeam | The dev team will create the preliminary documents of the system. | 1. Create Product backlog and Sprint Backlogs for estimation of Project Work. | 6 | 10 | 0 | 16
TMS | 1 | End User | As an end user I will be able to view the home page and exploit various other options present there. | 1. Design the Graphical User Interface of the home page. 2. Obtain the content that gives the overview of the entire website 3. Provide several other options related to travel and tourism. 4. Create a link to the 'About Us' , 'Find Placel Page, 'Registration' Page, 'Login' Page., Gallery' and 'contact us' page, feedback form page, and booking page. | 10 | 23 | 3 | 36
TMS | 2 | End User | As an end user I will be able to go to the 'about us' page of the website and gather information about it. | 1. Design the GUI of the 'About Us' page. 2. Obtain the information that gives the overview about the website and specifies its features. | 3 | 10 | 6 | 19
TMS | 2,3 | Admin | The admin has to create databases that store information entered by the user. Information has to be retirved when required | 1. Create a database that consists of 4 tables which are user table, places table, feedback table and booking table. 2. The user table consists of the id, name, phone, e-mail and password 3. The places table consists the id, title and image. 3. The booking table will consist of the place to be visited, the budget, the preferred mode of conveyance and the date of travel. (User ID : foreign key) 4. The feedback table consists of the comment column ( User ID: foreign key) | 8 | 22 | 6 | 36
TMS | 3 | End User | As an end user I should be able to register to the website by entering necessary details | 1. Create a registration form for the user. With fields 'Full name', 'Phone number'. , 'email-id' and 'password'. 6. The information is added in the user database. | 3 | 12 | 5 | 20
TMS | 3 | End User | As an end user I should be able to sign in with the information I registered with. | 1. Create a sign in page where user can login using email id and pasword 2. Create a 'email id' field and a password field. 3. Redirect to login page again if email id or password is wrong 4. Send an e-mail to registered email id if password is forgotten 5. Provide for a captcha enabled login | 2 | 15 | 5 | 22
TMS | 5 | End User | The Travel Planner will allow the end user to find places that they want to travel based on the entries that they will provide like the type of destination and number of persons travelling. | 1. Provide a drop down list for the type of destinations availabe so that the user can select a desired location. 2. Provide a textbox for the user to fill in the number of people travelling. 3. Create a submit button which will Store these details into the database., According to these details a list of different places will be displayed to the user. | 4 | 15 | 6 | 25
TMS | 6 | End User | As an end user I will be able to visit the gallery and the contact page and view details present there. | 1. Create the gallery page that consists several pictures of places that can be visited by the end user. 2. Create the contact us page that allows the user to call the travel agent directly. 3. Create the contact us page that allows the user to email the travel agency directly | 4 | 15 | 4 | 23
TMS | 7 | End User | The travel planner will allow the end user to book tickets for the destination that they want to travel. | 1. Create a form which will ask the user to enter details to book the ticket. by entering "place to be visited", "date of travel"., "mode of conveyance"., budget". 2. Save these details into the user database which has a booking table 3. The travel agent will then use this table to book the ticket independently. | 4 | 15 | 4 | 23
TMS | 8 | End User | As an end user I should be able to provide feedback and register the complaint. | 1. Create a feedback form for each user. 2. Add the feedback information to the database for review. 3. Create a complain/help box for the end user to send an e-mail to the travel agent incase required. | 5 | 15 | 5 | 25
Total Hours |  |  |  |  | 49 | 152 | 44 | 245
Signature (Project Guide) |  |  |  | Signature ( Scrum Master) |  | Signature (Project Coordinator)